## Sheet1
Task | Assigned To | Completed By
REQUIREMENTS
Introduction | Grace Daily | Grace Daily
Context Diagram | Cody Mercer / Ammar Rafiq | Cody Mercer / Ammar Rafiq
User Interface (lobby and leaderboard) | Subodh Neupane | Subodh Neupane
User Interface | Subodh Neupane | Subodh Neupane
System Requirements (write requirements) | Will Maberry | Will Maberry
System Requirements (remaining parts of spreadsheet) | Will Maberry | Will Maberry
Unknown List | Ammar Rafiq | Ammar Rafiq
Review for consistency and completeness | Grace Daily | Grace Daily
DESIGN
Class Diagram | Will Maberry | Will Maberry (approved by group)
Leaderboard and Lobby Classes | David Oyekola | David Oyekola
Players and Wordbank Classes | Subodh Neupane | Subodh Neupane
GameSession Class | Grace Daily | Grace Daily
WordBankGame Class | Cody Mercer | Cody Mercer
UserAuthentication Class | Will Maberry | Will Maberry
Overlooked All Classes | Ammar Rafiq | Ammar Rafiq
Updated Task Requirements and Project Requirements | Will Maberry | Will Maberry
IMPLEMENTATION
Updated Task Requirements and Project Requirements | Will Maberry | Will Maberry
WordList.txt | Will Maberry | Will Maberry
WordLocation.java | Will Maberry | Will Maberry
WordBank.java (and associated unit tests) | Will Maberry | Will Maberry
GameSession.java (and associated unit tests) | Will Maberry | Will Maberry
Index.html | David Oyekola | David Oyekola and Will Maberry
WordBankGame.java | David Oyekola | Didn't end up needing
Deployed to cse3310.org | David Oyekola | David Oyekola
App.java | Grace Daily | Grace Daily and Will Maberry
ServerEvent.java | Grace Daily | Grace Daily
UserAuthentication.java (and associated unit tests) | Ammar Rafiq | Ammar Rafiq
UserEvent.java | Ammar Rafiq | Ammar Rafiq and Will Maberry
Lobby.java (and associated unit tests) | Subodh Neupane | Subodh Neupane
Leaderboard.java (and associated unit tests) | Subodh Neupane | Subodh Neupane
Players.java (and associated unit tests) | Cody Mercer | Cody Mercer
Statistics.java (and associated unit tests) | Cody Mercer | Cody Mercer