## Sheet1
Task | Assigned To | Completed By
REQUIREMENTS
Introduction | Grace Daily | Grace Daily
Context Diagram | Cody Mercer / Ammar Rafiq | Cody Mercer / Ammar Rafiq
User Interface (lobby and leaderboard) | Subodh Neupane | Subodh Neupane
User Interface | Subodh Neupane | Subodh Neupane
System Requirements (write requirements) | Will Maberry | Will Maberry
System Requirements (remaining parts of spreadsheet) | Will Maberry | Will Maberry
Unknown List | Ammar Rafiq | Ammar Rafiq
Review for consistency and completeness | Grace Daily | Grace Daily
DESIGN
Class Diagram | Will Maberry | Will Maberry (approved by group)
Leaderboard and Lobby Classes | David Oyekola | David Oyekola
Players and Wordbank Classes | Subodh Neupane | Subodh Neupane
GameSession Class | Grace Daily | Grace Daily
WordBankGame Class | Cody Mercer | Cody Mercer
UserAuthentication Class | Will Maberry | Will Maberry
Overlooked All Classes | Ammar Rafiq | Ammar Rafiq
Updated Task Requirements and Project Requirements | Will Maberry | Will Maberry